## Sheet1
Q | A
What is the role of the Scrum Master? | The scrum master is the leader as well as coach of the Scrum team. The scrum master is responsible to serve and protect his team from any kind of distractions that could affect their performance. The main role of the scrum master is to motivate his team to achieve the sprint goal. He is focused to build a self-organized and motivated team where each member is familiar with the implementation of Agile and Scrum principles and applications. The scrum master keeps a proper check on the scrum team if they are executing committed tasks properly. He is also responsible to increase the efficiency and productivity of the team so that they can achieve the sprint goal effectively.
What is the duration of a scrum sprint? | Generally, the duration of a scrum sprint (scrum cycle) depends upon the size of project and team working on it. The team size may vary from 3-9 members. In general, a scrum script complete in 3-4 weeks. Thus, on an average, the duration of a scrum sprint (scrum cycle) is 4 weeks. This type of sprint-based Agile scrum interview questions is very common in an agile or scrum master interview.
What is agile approch? | It is an approach mainly used for software development. In this methodology, complex projects are broken down into smaller units that are achievable in a specific time frame. It always involves customers in the development process.
What is Agile Manifesto? | The agile manifesto is basically a document consisting of values and principles that are expressed in Agile
What is Burn-up chart in Agile? | It is a type of chart that is used to display or represent the amount of work that has been completed and the total amount of work for a sprint or iteration.
What is Burn-down charts in Agile? | It is a type of chart that is used to display or represent the amount of work that is remaining to be completed in the project. These charts are very simple and easy to understand
What is “Planning Poker” technique? | Planning Poker, also known as Scrum Poker, is a consensus-based technique that not only helps agile teams to estimate the time and effort that is required to complete each initiative on their product backlog but also identifies issues before time and within the course of a user story. It makes the meeting more short, productive and creates estimates with the involvement of the whole team. It is mainly used to avoid the influence of other participants, and force each person to think independently and give their opinion.
What is Sprint Planning Meeting | In this meeting, the discussion takes place about features and product backlog items (user stories) that are important to the team. This meeting is usually attended by the product owner, Scrum Master and Scrum Team. It is a weekly meeting and usually lasts for about an hour
What is Sprint Review Meeting | In this meeting, the Scrum team gives a demonstration of the product. After this, the product owner determines which items completed and which are not completed. He also adds some additional items to the product backlog on the basis of feedback from customers or stakeholders. Its main aim is to inspect the product being created in the sprint and modify it if required.
What is Sprint Retrospective Meeting | This meeting takes place after the Sprint planning meeting. In this meeting, the Scrum team meets again to inspect itself and discuss the past mistakes, potential issues and methods to resolve them. Main aim of this meeting is to improve the development process. This meeting lasts for about 2-3 hours.